## Sheet1
LOG OF RISKS
Matthew Anthony James Hawkins
UP769535
A flashcard web application to help efficiently learn Japanese
Status | Risk Impact | Risk Probability | Risk Description and Type | Risk Impact to Project | Indicators and Causes | Mitigation | Solution if Risk Occurs
Open | High | Low | Loss of all project data | Project has to be started from scratch or from earlier start point. Completely wastes time and will add huge pressure and stress causing a bad project. | Hardware/software failures. Failure to create regular backups or pushes to Github. | Regular saving, backups and use of Github to prevent complete data loss. | Resort to most recent backup of work. Note down as much information that can be remembered as possible and attempt to add back into project. Re-do work that has to be done again.
Open | Medium | Low | Loss of web hosting | No live version means no testing can be done. | Run out of funding. Infringement of web host's ToS. DDOS or similar attacks. | Keep track of funding. Read web host's ToS before hosting project. Consider security risks. | Attempt to talk with hosting service to re-instate hosting. If this fails then go with a different provider. If funding runs dry then get free hosting, or resort to a local environment for testing as well.
Open | Low | Low | Web hosting downtime | No live version means no testing can be done. | Contact from web hosting company about downtime. | Have a flexible schedule. | Adjust schedule.
Open | Medium | Medium | Risk of not meeting the schedule | Work isn't completed on time and affects the amount of work that can get done within the given timeframe. This can also reduce the overall quality. | External factors such as possible issues with family/friends/health or other coursework/projects. Literally any external factor that isn't related directly to the project but that could take time away from it. | Create and stick to a tight schedule with deadlines. | Take time away from external factor and put extra time into project in order to meet schedule deadlines.
Open | High | Medium | Development of "spaghetti code" i.e. producing bad code that could cause issues further into the project. | Depending on what and where this is done, it could cause minor issues or it could prevent the entire system from functioning properly, resulting in huge changes in code. | Taking shortcuts/getting lazy when programming. Not sticking to design documentation. | Be mindful of best practices when coding. Stick to documentation. | Fix code immediately.
Open | Low | Low
Open | Low | Low
|  | Open | High
|  | Closed | Medium
Low